## Tasks
Project tracker
Yellow cells are inputs. Duration, days left and the Gantt bars are calculated — the bars are conditional formatting, not shapes.
Timeline starts | 2026-08-31 | Today | 2026-09-11 | Type =TODAY() in D3 to keep it live
Phase | Task | Owner | Start | End | Status | Done | Days | Left
Discovery | Stakeholder interviews | Priya | 2026-08-31 | 2026-09-11 | Done | 100%
Discovery | Support inbox review | Priya | 2026-09-07 | 2026-09-16 | In progress | 60%
Discovery | Research report | Priya | 2026-09-17 | 2026-09-23 | Not started | 0%
Design | Flows and wireframes | Mara | 2026-09-14 | 2026-10-02 | In progress | 30%
Design | Visual design | Mara | 2026-10-05 | 2026-10-23 | Not started | 0%
Design | Usability test round 1 | Priya | 2026-10-12 | 2026-10-16 | Not started | 0%
Build | API and data model | Teo | 2026-09-21 | 2026-10-16 | In progress | 20%
Build | Onboarding screens | Jonas | 2026-10-12 | 2026-11-06 | Not started | 0%
Build | Payments integration | Teo | 2026-10-19 | 2026-11-13 | Blocked | 0%
Build | Admin dashboard | Jonas | 2026-11-02 | 2026-11-20 | Not started | 0%
Launch | QA and bug bash | Jonas | 2026-11-16 | 2026-11-27 | Not started | 0%
Launch | Beta with 20 customers | Mara | 2026-11-23 | 2026-12-11 | Not started | 0%
Launch | Public launch | Teo | 2026-12-14 | 2026-12-18 | Not started | 0%
Bars: light = planned, solid = the done share (from the Done column), red = blocked. The red line is the week containing Today.
Add a task: type in any empty row down to 60. Insert rows inside the block for more; the bars extend.
Template by Foldout · foldoutkit.com